## Sheet1
Strategic Plan
| 1 | Grants Writing |  | Completion Date
| 1.1 | Evaluate Current Process for the need and purpose of drafting a grant | Frank Andrews Jr./Tribal Programs | Completed 10/1/13
| 1.2 | Determination of need by Public Input Meetings/CEDS/or Reservation disaster | Tribal Council/Programs/Priority | In Development Stage
| 1.3 | Incorporate the Grant Selection Process by tribal resolution | Execuative Director/Tribal Council Resolution | Project by project
| 1.4 | Announce Grant Drafting Process to all tribal programs/employees by tribal broadcast | Execuative Director/Tribal Council Resolution | Completed 1/16/14
| 1.5 | Monitor the approved grant selection process and if need be, ititiate positive changes | Frank andrews/Lisa True | Completed 1/16/14
| 2 | Grant Guidelines
| 2.1 | Spell out the project requirements and deliverables. | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 2.2 | Planning the Grant Budget. | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 2.3 | Salaries/Fringe/Benefits/ & Insurance | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 2.4 | Equipment-detail | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 2.5 | Travel-detail | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 2.6 | Materials & Supplies-detail | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 2.7 | Contracts/Facility/Administrative Costs (aka overhead/Indirect) | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 2.8 | Cost sharing/Matching/In-kind. | Lisa True/Frank Andrews Jr. Grant Workshop | Grant Workshop 1/16/14
| 3 | Grant Roles & Responsibilities:
| 3.1 | Administration and Fiscal Management/Terms and Conditions of the award | Program Manager/Comptroller' Office | On going process
| 3.2 | Project work performance/ensures deliverables/what is allowable | Program Manager/Comptroller' Office | On going process
| 3.3 | Monitors Grant Activity for compliance with award requirements. | Grant Compliance Officer/Comptrollers Office | On going process
| 3.4 | Works closely with Contracts and Grants Compliance Officer re: reports | Program Manager/Comptroller' Office | On going process
| 4 | Grants Compliance Officer:
| 4.1 | Grant Review/Completeness in accounting/Program necessity of grant submission
|  | Proper submission of federal/state/or foundation grants | Grant Complince Officer | On going process
| 4.2 | Ensures proper financial management of projects and grant awards. | Grant Complince Officer | On going process
| 4.3 | Participates with tribal personnel engaged in specialized fiscal and grant |  | On going process
|  | regulatio compliance operation. | Grants Compliance Officer | On going process
| 4.4 | Coordinates/assists in preparation of required financial reporting. | Grants Compliance Officer | On going process
| 5 | Grants Administration: Preparing and Submitting Grant Proposals. | Frank Andrews Jr./Lisa True | On going process
| 5.1 | Program project need or concept for consideration | Tribal Programs | On going process
| 5.2 | Funding Search, State/Federal/Foundations | Frank Andrews/Lisa True | On going process
| 5.3 | Present proposal to appropriate council committee for review and approval | Frank Andrews/Lisa True | On going process
| 5.4 | Proposal Creation/Drafting | Frank Andrews/Lisa True | On going process
| 5.5 | Final review of draft grant document | Frank Andrews/Lisa True | On going process
| 5.6 | Grant Approval by Tribal Council Resolution | Frank Andrews/Lisa True | On going process
| 5.7 | Grant Submission | Frank Andrews/Lisa True | On going process
| 5.8 | Funding Agency Review/Determinations | Federal/State/Private funding agency's | On going process
| 5.9 | Award Negotiation and Contracting | Tribal Programs/Grants Officer | On going process
| 5.91 | Setting up award | Tribal Comptroller | On going process
| 5.92 | Drafting Grant Work Plans | Tribal Programs Administering Grant | On going process
| 5.93 | Grant Monitoring/Quarterely/Final Reporting | Tribal Programs Administering Grant | On going process
| 5.94 | Close out and audit of grant | Tribal Programs/Comptroller/Grants Officer | On going process